# Audience Post-mortem

### Overview

In Q1 2023, we worked to integrate LiveRamp to our marketing platforms. This allowed us to partner with AB teams outside of our immediate channels team, each with their own specific marketing goals. Our aim was to develop paid marketing strategies that were more tailored to our partner teams’ goals. We conducted testing from March to June 2023 until an unforeseen U.S. privacy law led us to suspend targeted campaigns (MarTech scoping in OP1).

LiveRamp is the data management platform our channel marketing group decided on. In collaboration with ABMA, the Paid Media team and the LiveRamp team, we constructed audience flows from our database, to S3, LiveRamp, and finally to our marketing platforms. The audiences (US-only) involved were:

- Verified US AB Registrants

- BCIvNext prospecting audience

- BP members

### Accomplishments:

- Developed relationships: Regular interaction between the marketing and technical teams during audience pipeline creation helped us to work with those on the technical end more regularly and candidly. Not only did this help to develop the audience pipelines but also helped us to work alongside each other and communicate fluidly.

- Tested our largest audience (AB registrants): We used our largest list in our partnership with the BP team to drive BP signups, and learned about this audience along the way. We created text ads for Brand paid search terms, BP terms, and more visual Discovery ads to drive traffic to the a.com/bp page, and drove a consistent amount of weekly signups to start. (average of 3 signups per week at a $600 CPA while account was being optimized) One learning is that consistent weekly signups were achieved through AB Brand terms, which accounted for 95% of spend.

- Tested a more limited prospecting audience (BCIvNext): This is also something we haven’t tested in Paid Search. Despite limited traffic volume, the accomplishment here was technical. We pulled data consistently from a Data Science propensity model that accesses A.com customer data.

### Challenges:

- Development and planning delays: Frequent pauses in progress while setting up LiveRamp. First, credentials errors connecting to LiveRamp’s instance of S3, which created pockets of time where nothing was moving. Second, I could have put more attention towards moving forward on the planning. (developing keyword lists, gathering creative, communicating to stakeholders to update on progress)

- Audience counts significant: Active users in our Google Ads were much lower than planned, which limited our available lists. Our AB Registrants list (largest list) was made up of 14 million users, but after delivering to Google Ads, only 1.7 million were active. (13% match rate) This was significantly lower than the 30-50% we expected. This limits us in terms of lists we could use. For example, the BCIvNext list, which was a highly anticipated list for the CPS team, started with 1.25 million users, and ended matching at 11% down to 140k active users on Google Ads.

  - For reference, the US CPS account used the 140k users BCIvNext audience, and spent just over $600 total in two months. In contrast, the BP account targeted the 1.7 million users in the All Registrants list and spent about $3k/week. Still relatively small compared to our SSR accounts (JP, our smallest SSR account, spends $3k/day in comparison) but this seems to be the volume we can get targeting Brand terms with 1st party data.

### Lessons Learned and Recommendations:

- Start simple, then go granular: We planned to launch 12 different audiences, and almost half were iterations of each other. For example, Verified US AB registrant, SMB all registrants, ENT all registrants (SMB and ENT are more granular lists contained within the Verified US AB registrants list) Faster progress could have been achieved by focusing on a few audiences at first.

  - This also applied to planning. Because our audience targeting campaigns weren’t structured tests, a simpler, iterative approach would likely have allowed us to launch earlier, and given us more time to learn/iterate.

- Landing page matters: The landing page experience should align with the search and ad text to drive more efficient results. Current testing shows higher CVRs when using cohesive experiences. We have run CPS paid search activity with/without targeting specific audiences, and with/without Enterprise-focused landing page. (Appendix B for data tables)

  - US CPS targeted the BCIvNext audience and didn’t have enough traffic volume to see performance. ($600 spend throughout 2 months)

  - CA CPS targeted CPS-focused keywords that attempt to qualify users, but send them to the A.com registration flow, where there is little context on the page, and the CPS CA account’s CVR was 83% lower than the CA SSR account’s (the SSR account focuses on SSR acquisition.)

  - EU’s CPS account targets CPS-focused keywords just like the CA account, but send users to a more familiar enterprise customer experience; a form fill to receive a whitepaper. This experience has a 32x higher CVR at driving MQLs/SQLs than the EU SSR accounts, which focus on SSR landing page experience. (Overall point is that a more cohesive experience from the search to the ad text to the landing page is likely to drive more efficient outcomes.)

- Brand terms: AB Brand terms hold the most influence in terms of cost and BP signups. When testing our largest 1st party audience with AB Brand terms, a couple sets of NB terms, BP terms, and Discovery ads, I found that AB Brand terms made up 95% of the cost, and 96% of all BP signups.

  - This means that the Registrants audience is still actively searching our brand terms, and priority should be on brand terms rather than specific AB features/AB products. (shipping, document storage, BP.)

  - A test for the future would also be product terms, to drive activation/retention goals.

### Appendix A: Reference Documents

LiveRamp Audience library: Paid Media and Paid Search

BP links:

- BP  Media Plan:  Initial strategy and tactics developed by PS and Product Marketing team,  and links to a more detailed plan.

- BP  Engagement Keywords

- BP  Dive Deep Report:  The tabs show performance for BP on PS accounts. High-level platform data  as well as data trends.

CPS links:

- EU CPS 2023

- CA CPS

- US CPS

### Appendix B:

Audience targeting (self-registration CPS)

vs. Qualifying keywords (self-registration CPS)

vs. Qualifying keywords (form fill lead generation)

US CPS: Audience targeting with SSR and CPS-qualifying keywords, driving for Self-registration CPS

SSR US: Keyword targeting driving for SSR registrations. (Keywords such as “Amazon Business” and “Office Supplies”)

|  | A | B | C |
| --- | --- | --- | --- |
| 1 | May to June 2023 | CPS US | SSR US |
| 2 | Cost | $621 | $5,650,919 |
| 3 | Clicks | 47 | 1,485,010 |
| 4 | SSR Registrations | 0 | 16,065 |
| 5 | CVR | 0% | 1.10% |
| 6 | CPA | - | $353 |
| 7 | Total MQL/SQL | 0 | 108 |

CA CPS: CPS-qualifying keyword targeting, driving for self-registration CPS

SSR CA: Keyword targeting driving for SSR registrations. (Keywords such as “Amazon Business” and “Office Supplies”)

|  | A | B | C |
| --- | --- | --- | --- |
| 1 | April to June 2023 | CPS CA | SSR CA |
| 2 | Cost | $26,181 | $766,934 |
| 3 | Clicks | 2,119 | 393,960 |
| 4 | SSR Registrations | 9 | 9,585 |
| 5 | CVR | 0.40% | 2.40% |
| 6 | CPA | $2,909 | $80 |
| 7 | Total MQL/SQL | 0 | 17 |

EU CPS: CPS-qualifying keyword targeting, driving for form fills (converted to MQL/SQL)

SSR EU: Keyword targeting driving for SSR registrations. (Keywords such as “Amazon Business” and “Office Supplies”)

|  | A | B | C |
| --- | --- | --- | --- |
| 1 | April to June 2023 | CPS EU | SSR EU |
| 2 | Cost | $141,692 | $4,645,263 |
| 3 | Clicks | 23,217 | 2,593,609 |
| 4 | SSR Registrations | 0 | 68,700 |
| 5 | CVR | 0% | 2.60% |
| 6 | CPA | - | $68 |
| 7 | Unique MQL/SQL | 13 | 43 |
| 8 | MQL+SQL CVR | 0.06% | 0% |
| 9 | MQL+SQL CPA | $10,900 | $108,029 |

*CPS EU: 39 unique MQLs+SQLs last quarter, and 13 uniques MQLs+SQLs that weren’t recycled or disqualified because of Tier, Invalid data, or other issues related to prospect quality.

*SSR EU: Although SSR doesn’t specifically drive for CPS and has worse CVR/CPA, it drove 2 Engagements and 1 Reengagement. (Quality) All Tier 3: 250MM-1.5B.